Planned Activities for the Search for the North Carolina A&T State University Chancellor.

| Activity | Timeline |
| --- | --- |
| - Search Advisory Committee Kickoff Meeting & Charge with UNC System President Hans. | November 6, 2023 |
| - Storbeck Search initial meeting with Search Advisory Committee | January 18, 2024 |
| - Listening Sessions with Internal and External Constituents (Online Survey Launched October 2023) | January 2024 |
| - Application collection with priority deadline on February 29th - Review, prioritization and selection for initial interviews - Conduct initial candidate interviews - Conduct campus interviews with internal and external stakeholders - Search Advisory Committee recommends three (3) unranked candidates to N.C. A&T Board of Trustees | Through April 2024 |
| - N.C. A&T Board of Trustees recommends three (3) unranked candidates to UNC System President - UNC System President interviews finalists - Background checks and due diligence conducted on candidates | April 2024 – May 2024 |
| - UNC System President recommends nominee to UNC System Board of Governors - UNC System Board of Governors elects new N.C. A&T Chancellor | May 2024 |